## Notes
Notes about this workbook

## Schedule
Senior design schedule
WBS | Task | Duration | Depends on | % complete | Owner | Pinned start | Start
1 | Planning | [5 empty] | 2026-10-05
1.1 | Define requirements | 5 |  | 40% | Sam
1.2 | Concept selection | 3 | 2SS | 12.5% |  | 2026-10-07
2 | Build & test
2.1 | Fabricate chassis | 8 | 3 | FALSE